## Project Proposal
Color Coding |  |  | Completed
|  |  | In Progress |  |  |  | Fall 2019 Semester
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2019-09-10 | 2019-09-17 | 2019-09-24 | 2019-10-01 | 2019-10-08 | 2019-10-15 | 2019-10-22 | 2019-10-29 | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | 2019-12-10 | 2019-12-17
Project Phase | Activity |  | Resource Type | Start Date | End Date | Progress %
Project Initiation | Project proposal discussion |  | All | 2019-09-15 | 2019-09-22 | 100%
| Prioritize project ideas |  | Mateo | 2019-09-15 | 2019-09-22 | 100%
| Estimation of cost and schedule |  | Matthew & Cesar | 2019-09-20 | 2019-09-27 | 100%
| Development of the business case |  | Matthew & Cesar | 2019-09-20 | 2019-09-27 | 100%
| Finalize PID documentation |  | All | 2019-09-27 | 2019-10-01 | 100%
MILESTONE 1: INITIAL PROJECT PLAN
Requirement Analysis | Production of project schedule |  | All | 2019-09-27 | 2019-10-04 | 100%
| Determine project features |  | Agil & Zixian | 2019-09-27 | 2019-10-04 | 100%
| Organize Project Team |  | Mateo | 2019-10-04 | 2019-10-11 | 100%
| Develop BRM Diagram |  | Matthew & Cesar | 2019-10-04 | 2019-10-11 | 100%
| Develop Context Diagram |  | Matthew & Cesar | 2019-10-04 | 2019-10-11 | 100%
| Define system requirements |  | Mateo, Zixian & Mingming | 2019-10-11 | 2019-10-18 | 100%
| Gathering of Business Requirements |  | Matthew & Cesar | 2019-10-11 | 2019-10-18 | 100%
| Requirements prioritization |  | Mingming | 2019-10-11 | 2019-10-18 | 100%
| Business Requirements |  | Matthew & Cesar | 2019-10-11 | 2019-10-21 | 80%
| RCT Documentation |  | Matthew | 2019-10-11 | 2019-10-21 | 100%
| Functional Decomposition |  | Matthew | 2019-10-11 | 2019-10-21 | 100%
| Fishbone Diagram Mapping |  | Matthew | 2019-10-11 | 2019-10-21 | 100%
| Functional Req. - User Stories |  | Agil | 2019-10-20 | 2019-10-27 | 100%
| UML diagrams (activity & use cases) |  | Jessica | 2019-10-20 | 2019-10-29 | 100%
| Data Flow Diagram |  | Mingming | 2019-10-20 | 2019-10-29 | 100%
| Implement module 1 (product listing) |  | Mateo & Agil | 2019-11-13 | 2019-11-27 | 50%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | ER diagrams (conceptual, logical) |  | Mateo | 2019-11-05 | 2019-11-12 | 100%
| Database table specs |  | Matthew | 2019-11-05 | 2019-11-12 | 100%
| Data flow diagram (physical) |  | Cesar | 2019-11-12 | 2019-11-19 | 100%
| Create webpage for product (1.01) |  | Mateo | 2019-11-13 | 2019-11-26 | 100%
| Design GUI of product listing (1.02) |  | Mingming | 2019-11-13 | 2019-11-26 | 100%
| Specify listing price (1.03) |  | Cesar | 2019-11-13 | 2019-11-26 | 100%
| Verify product quantity available (1.04) |  | Zixian | 2019-11-13 | 2019-11-26 | 100%
| Architecture diagrams (2) |  | Jessica | 2019-11-12 | 2019-11-19 | 100%
| Class diagram |  | Matthew | 2019-11-19 | 2019-11-26 | 100%
| Sequence diagram |  | Cesar | 2019-11-13 | 2019-11-20 | 100%
| Test plan |  | Matthew | 2019-11-26 | 2019-12-03 | 50%
| Test design |  | Jessica | 2019-11-26 | 2019-12-03 | 50%
MILESTONE 3: DESIGN COMPLETED
Code | Create webpage for product (1.01) | GUI & Functionality Design | Agil & Jessica | 2019-11-13 | 2019-11-27 | 50%
|  | Coding | Mateo | 2019-11-13 | 2019-11-27 | 50%
| Design GUI of product listing (1.02) | GUI & Functionality Design | Agil & Jessica | 2019-11-13 | 2019-11-27 | 50%
|  | Coding | Mateo | 2019-11-13 | 2019-11-27 | 50%
| Specify listing price (1.03) | GUI & Functionality Design | Zixian & Mingming | 2019-11-13 | 2019-11-27 | 50%
|  | Coding | Jessica | 2019-11-13 | 2019-11-27 | 50%
| Verify product quantity available (1.04) | GUI & Functionality Design | Zixian & Mingming | 2019-11-13 | 2019-11-27 | 50%
|  | Coding | Jessica | 2019-11-13 | 2019-11-27 | 50%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Overall Testing Strategy |  | All | 2019-11-19 | 2019-12-03 | 50%
| Evaluate Features to be Tested |  | All | 2019-11-19 | 2019-12-03 | 50%
| Create webpage for product (1.01) | Design Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Execute Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Anaylze Test Results | All | 2019-11-19 | 2019-12-03 | 50%
| Design GUI of product listing (1.02) | Design Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Execute Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Anaylze Test Results | All | 2019-11-19 | 2019-12-03 | 50%
| Specify listing price (1.03) | Design Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Execute Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Anaylze Test Results | All | 2019-11-19 | 2019-12-03 | 50%
| Verify product quantity available (1.04) | Design Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Execute Test Cases | All | 2019-11-19 | 2019-12-03 | 50%
|  | Anaylze Test Results | All | 2019-11-19 | 2019-12-03 | 50%
Implementation | Deploy Website For Presentation Demo |  | All | 2019-12-10 | 2019-12-17 | 20%
MILESTONE 5: TESTING COMPLETED
Presentation | Prepare Presentation of Demo |  | All | 2019-12-10 | 2019-12-17 | 0%
Formulas:
End Date = [Start Date]+7
Start Date = [Start Date, row above]+7
Start Date = [Start Date, row above]